## Tasks (ClickUp Import)
Task ID | Task Name | List | Description | Status | Priority | Sequence Group | Story Points | Tags | Area | Surface | Dependencies | ClickUp Task ID | ClickUp URL | ClickUp Assignee | ClickUp Status | Assigned to Me
CC.1 | CC.1 — Add “definition of sharp” checklist to PR template | Cross-cutting — Sharpen features (quality bar) | This item (“Sharpen Features”) isn't a standalone feature — it's a quality bar that should apply to every epic in this plan. Turn it into something enforceable: add a lightweight “definition of sharp” checklist to the PR template covering acceptance criteria met, no regression to adjacent features, designed empty/error/loading states, and (for AI output) a visible confidence/source. Acceptance criteria: (1) PR template includes a checklist item: acceptance criteria met (not just demoed). (2) PR template includes a checklist item: no regression to an adjacent existing feature. (3) PR template includes a checklist item: empty/error/loading states designed, not just the happy path. (4) PR template includes a checklist item: AI-generated output includes a visible confidence or source per the product's AI guardrails. | to do | Normal | 1 | 2 | platform,docs | platform | backend,frontend | none |  |  |  |  | No
R17.1 | R17.1 — Notification center (in-app) | R17 — Notifications, SDR reminders & auto-alerts | Skout has no notification system today. Build the foundational piece: a central notifications store and an in-app UI (bell icon, unread count, feed) that every other alert type in this plan (list refresh, signal alert, task reminder) will plug into. Acceptance criteria: (1) A notifications table records type, the entity it's about, read/unread state, timestamp, and who it's scoped to. (2) The in-app bell + feed supports marking as read and filtering by type. (3) The type field is an extensible enum so new alert kinds can be added without a schema change. | to do | High | 1 | 8 | platform,backend,frontend | platform | backend,frontend | none — the foundation other epics build on |  |  |  |  | No
R21.1 | R21.1 — Task entity + CRUD API | R21 — Tasks | Skout doesn't have a native task object today, even though “Task” is listed as a core entity in the product's data model. Build it: a real table with type (call/email/follow-up/custom), due date, owner, an optional link to a prospect/company/deal, and a status lifecycle. Acceptance criteria: (1) POST/PATCH/DELETE /tasks is workspace-scoped and lets a task be assigned to any workspace member. (2) A task can optionally link to a prospect/company via entityType + entityId. (3) Status moves from open to done or skipped, and completedAt is recorded. | to do | High | 1 | 5 | platform,backend | platform | backend | none — new foundational schema several other epics depend on |  |  |  |  | No
R10.1 | R10.1 — Smart lists as the default list-creation path | R10 — Kill Static List (dynamic-by-default lists) | Change the “New list” creation flow (UI + POST /lists) so it defaults to building a smart list (filter-based, dynamic) instead of a static, manually-curated list. Static list creation should still be possible for CSV imports and one-off manual adds, but must require an explicit “advanced/manual” toggle rather than being the default path. Acceptance criteria: (1) POST /lists default flow creates a smart_lists filter set, not a bare static list. (2) Static list creation still available under an explicit opt-in for imports/manual adds. (3) Existing static lists are unaffected — this is an additive UI/default change, not a data migration. | to do | High | 2 | 5 | prospecting,backend,frontend | prospecting | backend,frontend | none (smart_lists table and API already exist) |  |  |  |  | No
R10.2 | R10.2 — Auto-refresh cadence for dynamic lists | R10 — Kill Static List (dynamic-by-default lists) | Dynamic (smart) lists currently only re-run their filters when a user manually clicks “run”. Add a configurable refresh schedule (e.g. daily/weekly) so a smart list's membership updates automatically, and show the user a diff of what was added/dropped since the last refresh. Acceptance criteria: (1) Each smart list has a configurable refresh interval. (2) Refresh runs on schedule via a background job. (3) UI shows a diff view (new members vs. dropped members) after each refresh. (4) Refresh is credit-aware — it skips (and notifies the user) rather than silently overspending if the workspace can't afford the credit cost. | to do | High | 2 | 8 | prospecting,backend | prospecting | backend | R10.1; R17.1 (notification center) |  |  |  |  | No
R11.2 | R11.2 — Unified signal store | R11 — Signal expansion (tech signals + overlays) | Signals currently live in several disconnected places (search-time filter fields, scraper output). Create one formal signals table/index — the Signal entity already named in the product PRD — so every kind of signal (intent, hiring, funding, leadership change, tech-stack change) is stored and queried the same way, instead of each feature inventing its own ad hoc field. Acceptance criteria: (1) A single schema stores signal_type, entity_id, value, confidence, detected_at, and provenance. (2) Existing signal sources (search filters, scraper collectors) are updated to write into this store instead of their own one-off fields. (3) GET /api/v1/signals?entityId= returns a normalized, chronological timeline of every signal for that entity. | to do | High | 2 | 5 | corpus,backend | corpus | backend | none — new shared infrastructure other signal work builds on |  |  |  |  | No
R13.1 | R13.1 — Auto re-score on ICP change | R13 — Automation core (auto-actions + auto-filled fields) | Right now, changing the workspace ICP does not retroactively re-score prospects that were already scored under the old ICP — a rep has to remember to click “Score all” again. Automate this: when the ICP changes, automatically queue a background job that re-scores every already-activated prospect. Acceptance criteria: (1) Saving a new ICP version automatically triggers a background re-score job, with visible progress and a toggle to disable it. (2) Both prospect_scores and the corpus document are updated with the new score. | to do | High | 3 | 8 | ai,backend | automation | backend | existing scoring API |  |  |  |  | No
R17.2 | R17.2 — Task/sequence reminders | R17 — Notifications, SDR reminders & auto-alerts | Generate reminders for things that need a human's attention: tasks approaching their due date, sequence steps that require manual action (like a LinkedIn touch), and drafts sitting too long in the review queue. Acceptance criteria: (1) A reminder is generated a configurable number of hours before (or at) something's due time. (2) The reminder auto-resolves once the underlying task/step is actually completed. | to do | Normal | 4 | 5 | platform,backend | platform | backend | R17.1 |  |  |  |  | No
R21.2 | R21.2 — Task views (My Tasks, due today/overdue) | R21 — Tasks | Give reps a place to actually see and manage their tasks: a “My Tasks” page across all their prospects, a dashboard widget showing what's due today/overdue, and the ability to add a task manually from any prospect/company detail page. Acceptance criteria: (1) “My Tasks” page filters by status, due date, and linked entity. (2) A dashboard widget shows tasks due today plus an overdue count. (3) “Add task” is available both from prospect/company detail and from within a sequence step. | to do | Normal | 4 | 5 | platform,frontend | platform | frontend | R21.1 |  |  |  |  | No
R21.3 | R21.3 — Tasks feed the notification/reminder system | R21 — Tasks | Connect tasks to the reminder system (R17.2) so they aren't two disconnected features — creating or editing a task's due date should automatically schedule the right reminder, and completing the task should cancel it. Acceptance criteria: (1) Creating or editing a task's due date auto-schedules an R17.1 notification. (2) Marking a task done or skipped cancels its pending reminder. | to do | Normal | 4 | 3 | platform,backend | platform | backend | R21.1; R17.1; R17.2 |  |  |  |  | No
R10.3 | R10.3 — Static-list deprecation path in UI | R10 — Kill Static List (dynamic-by-default lists) | Nudge users away from static lists without removing the feature outright. Add a “Convert to dynamic list” action on existing static lists where the list's original filters can be reconstructed, and change onboarding/empty-state copy so new users are guided toward building a dynamic (smart) list first. Acceptance criteria: (1) Static list detail page shows a one-click “Convert filters to smart list” action when feasible. (2) The empty state for “create your first list” defaults to the smart-list flow, with static list as a secondary link. | to do | Normal | 5 | 3 | prospecting,frontend | prospecting | frontend | R10.1 |  |  |  |  | No
R13.2 | R13.2 — Auto-route AI drafts by score/segment | R13 — Automation core (auto-actions + auto-filled fields) | Every AI-generated outreach draft currently goes into the same human-review queue regardless of how strong the match is. Add a rule-based routing layer so obviously strong-fit, low-risk drafts can be auto-approved, while everything else still requires a human to review before it can be sent. Acceptance criteria: (1) Workspace admins can set an auto-approve threshold (ICP score + AI confidence) plus an always-review list/segment that bypasses auto-approval. (2) Auto-approved drafts are still visible in the review queue, tagged “auto-approved,” for a full audit trail. | to do | Normal | 5 | 5 | ai,automation,backend | automation | backend | existing AI review queue |  |  |  |  | No
R17.3 | R17.3 — Signal-triggered SDR alerts (auto-alert) | R17 — Notifications, SDR reminders & auto-alerts | When a qualifying signal fires on an account an SDR owns — a funding event, new tech adoption, an intent spike — automatically notify that SDR instead of relying on them to notice it themselves while browsing. Acceptance criteria: (1) An alert rule pairs a signal type + threshold with “notify the owning SDR.” (2) Users can choose real-time alerts or a daily digest rollup. (3) Every alert links directly to the account/signal detail so the SDR can act on it immediately. | to do | Normal | 5 | 5 | platform,ai,backend | platform | backend | R17.1; R11.2 |  |  |  |  | No
R17.4 | R17.4 — Email/Slack delivery channel | R17 — Notifications, SDR reminders & auto-alerts | In-app notifications only reach a user who's logged in. Add delivery outside the app — at minimum email, and Slack if the workspace has it connected — for high-priority alerts, so an SDR doesn't miss a hot signal just because they weren't in the tab. Acceptance criteria: (1) Each notification type has a per-user channel preference (in-app / email / both). (2) If outside delivery fails, that never blocks the in-app notification from being created. | to do | Normal | 5 | 5 | platform,backend | platform | backend | R17.1 | 86d3wzjzb | https://app.clickup.com/t/90161651543/86d3wzjzb | Neeraj Singh | to do | Yes
R22.1 | R22.1 — Apollo.io connect + contact/list import | R22 — GTM platform import (Apollo.io + others) | Apollo.io is already used internally as a paid data provider inside Skout's enrichment waterfall — this is a completely separate, new capability: let a user connect their own Apollo.io account and import their existing contacts and saved lists into Skout, so they can migrate off Apollo without manually re-entering their pipeline. Use a different credential path than the existing internal Apollo enrichment key. Acceptance criteria: (1) The connect flow stores the user's own Apollo API key encrypted, the same way BYOK integration keys are handled today. (2) Import pulls contacts/saved lists, activates them in Skout, and adds them to a chosen Skout list. (3) Prospects are matched against the existing prospect_id identity so re-importing doesn't create duplicates. | to do | Normal | 6 | 8 | platform,backend,integrations | platform | backend | none — reuses existing BYOK and activation patterns |  |  |  |  | No
R22.2 | R22.2 — Generic GTM-provider import framework | R22 — GTM platform import (Apollo.io + others) | Rather than hand-building a one-off import pipeline for every new tool, generalize the pattern behind both the existing HubSpot import and the new Apollo import (R22.1) into one shared adapter interface, so adding a third provider (Outreach.io, Salesloft, Snov.io) later doesn't require rebuilding the whole pipeline. Acceptance criteria: (1) A shared ImportAdapter interface defines listContacts(), listLists(), and mapToProspectCandidate(). (2) HubSpot and Apollo both implement it; adding a third provider requires no changes to the core import pipeline, only a new adapter. | to do | Normal | 6 | 5 | platform,backend | platform | backend | R22.1 |  |  |  |  | No
R12.1 | R12.1 — TAM definition from ICP | R12 — Build TAM (Total Addressable Market) | Give users a way to define and save a Total Addressable Market — the full set of accounts that match their Ideal Customer Profile — as a persistent, named object, distinct from a one-off search. This turns the ICP filters into a sized, trackable universe rather than something a user has to re-search every time. Acceptance criteria: (1) POST /tam builds a named TAM using the current workspace ICP (or a custom filter override). (2) Response returns the total addressable account count plus a segment breakdown by industry/size/geo. (3) The TAM is persisted and can be re-computed later — not just a one-time snapshot. | to do | Normal | 7 | 8 | prospecting,backend | prospecting | backend | existing ICP settings; existing corpus search |  |  |  |  | No
R12.2 | R12.2 — TAM coverage & fill-rate tracking | R12 — Build TAM (Total Addressable Market) | Once a TAM exists, track how much of it the team has actually worked — what percentage is activated, enriched, contacted, or has become a deal — so RevOps/leadership can see real market penetration instead of just a raw account count. Acceptance criteria: (1) TAM detail view shows a coverage funnel: total accounts → activated → enriched → contacted → replied → deal. (2) The funnel recomputes automatically whenever the TAM refreshes. | to do | Normal | 7 | 5 | analytics,backend | prospecting | backend | R12.1; R10.2 |  |  |  |  | No
R12.3 | R12.3 — TAM view UI (map/table) | R12 — Build TAM (Total Addressable Market) | Build the dedicated workspace page where a TAM actually lives: a segment breakdown table with the option to overlay signals, and the ability to drill into any segment as a live, filtered dynamic list that can be exported or pushed straight into a sequence. Acceptance criteria: (1) Segment breakdown table supports drilling into a segment as a filtered dynamic list. (2) The signal-overlay toggle from R11.3 is available on this view. (3) A segment (or the whole TAM) can be exported as CSV or pushed directly into a sequence. | to do | Normal | 7 | 8 | frontend,prospecting | prospecting | frontend | R12.1; R11.3 |  |  |  |  | No
R11.1 | R11.1 — Tech-stack change signals (adopted/dropped) | R11 — Signal expansion (tech signals + overlays) | Today the corpus detects a company's tech stack as a point-in-time snapshot at scrape time. This task adds change detection: when a re-crawl of a company finds a different tech stack than the last stored snapshot, generate a typed signal recording what was added or dropped, when, and from which source. Acceptance criteria: (1) signals[] on the prospect/company record includes tech_adopted / tech_dropped entries with tool name, detected date, and source. (2) A signal is generated automatically whenever a re-crawl finds a delta vs. the previous snapshot (not on every crawl, only on change). (3) The new signals show up in prospect/company detail and are usable as a search filter. | to do | Normal | 8 | 8 | corpus,backend | corpus | backend | R6.3, R6.5 (existing corpus/crawl pipeline) |  |  |  |  | No
R11.3 | R11.3 — Signal overlay UI | R11 — Signal expansion (tech signals + overlays) | Signals are currently buried inside a search filter panel. Add a visual overlay — badges/icons for funding, hiring, tech-stack change, and intent spikes — directly on company/prospect cards, list views, and the TAM view, so a rep can see what's happening with an account at a glance instead of digging through filters. Acceptance criteria: (1) Company/prospect card shows up to the 3 most recent/relevant active signals as badges, with how recently each was detected. (2) List and TAM table views have a toggle to show a “signals” column. (3) Clicking a badge opens a detail popover showing the signal's source, date, and confidence. | to do | Normal | 8 | 5 | frontend,corpus | corpus | frontend | R11.2; R12 (TAM view is one place this renders) |  |  |  |  | No
R18.1 | R18.1 — Engagement-decay risk flag | R18 — Risk detection | Flag accounts/prospects whose engagement is trending down — no opens, replies, or activity over a rolling time window — as at-risk, using activity data Skout already has (sequence steps, inbox threads, enrichment history). This is the first, simplest risk signal; it needs no new data sources. Acceptance criteria: (1) A risk score is computed from how recent and how frequent an account's engagement events are. (2) The resulting flag is surfaced on the prospect/company detail page and feeds into the R17.3 alerting pipeline. | to do | Normal | 9 | 8 | ai,backend | ai | backend | existing sequence tracking (open/click); existing inbox thread state |  |  |  |  | No
R18.2 | R18.2 — Negative-signal risk flag | R18 — Risk detection | Add a second, distinct category of risk beyond simple engagement decay: detect risk-indicating signals like a leadership departure at a target account, negative sentiment detected in a reply, or budget-freeze language — and surface each with a plain-language reason, not just an opaque score. Acceptance criteria: (1) At least 2 risk-signal types beyond engagement decay are live. (2) Every risk flag includes a plain-language explanation of why it was raised, not just a number. | to do | Normal | 9 | 8 | ai,backend | ai | backend | R11.2; existing reply/thread sentiment tagging |  |  |  |  | No
R13.3 | R13.3 — Auto-filled CRM/contact fields | R13 — Automation core (auto-actions + auto-filled fields) | When enrichment, meeting notes, or call notes produce structured information about a prospect (title changes, stated budget, next steps, etc.), that data should populate the relevant contact/company fields automatically instead of requiring someone to type it in by hand. Always show where an auto-filled value came from, and always let a human's manual edit win. Acceptance criteria: (1) Auto-fill writes into the prospect's snapshot record with a source (enrichment / meeting_bot / call_note) and a confidence value. (2) Auto-filled fields are visually distinguished in the UI from fields a human typed in. (3) A user's manual edit is never silently overwritten by a later auto-fill. | to do | Normal | 10 | 8 | automation,backend,frontend | automation | backend,frontend | existing enrichment pipeline; R16.2; R20.1 | 86d3wzjzw | https://app.clickup.com/t/90161651543/86d3wzjzw | Neeraj Singh | to do | Yes
R13.4 | R13.4 — Auto-activation rules (score threshold → action) | R13 — Automation core (auto-actions + auto-filled fields) | Let a workspace define simple, explicit rules that trigger an action automatically once a prospect crosses a score threshold or matches a signal — e.g. “score ≥ 80 and hiring signal present → auto-enroll in this sequence.” This is a small, fixed rule engine, not a general workflow builder — capped so it can't run away unsupervised. Acceptance criteria: (1) A rule combines a score threshold and/or a signal match with a target action (activate, add to list, enroll in sequence). (2) A workspace can have at most 5 active rules at a time (safety guardrail). (3) Every action a rule takes is logged and can be manually reversed (unenroll, remove from list). | to do | Normal | 10 | 8 | automation,backend | automation | backend | R13.1; existing sequence enrollment API | 86d3wzjzv | https://app.clickup.com/t/90161651543/86d3wzjzv | Neeraj Singh | to do | Yes
R20.1 | R20.1 — Call notes capture | R20 — Notes, suggestions & calling (Sales + Marketing) | Add the ability to attach call notes — manual, or auto-transcribed where available — to a prospect/company's activity timeline. This should be usable by both sales and marketing users, and not tied specifically to a sequence step, since not every call happens as part of a cadence. Acceptance criteria: (1) A note entity supports channel = call, free text, and optional structured tags (outcome, next step). (2) Notes appear on the unified activity timeline alongside emails and meetings, not in a separate silo. | to do | Normal | 11 | 5 | platform,backend,frontend | platform | backend,frontend | none — can ship ahead of the Twilio dialer integration |  |  |  |  | No
R20.2 | R20.2 — Dialer/calling integration (Twilio) | R20 — Notes, suggestions & calling (Sales + Marketing) | Wire up click-to-call from a prospect's record using Twilio (already on the platform's MVP integration list), so a rep can dial directly from Skout instead of switching to another tool, and have the call's duration/outcome logged automatically. Acceptance criteria: (1) Click-to-call initiates the call via Twilio and logs it with duration and disposition automatically, no manual re-entry. (2) The recording (where legally permitted in that jurisdiction) attaches to the corresponding note. | to do | Normal | 11 | 8 | platform,backend,infra | platform | backend,infra | R20.1 | 86d3wzjzy | https://app.clickup.com/t/90161651543/86d3wzjzy | Neeraj Singh | to do | Yes
R20.4 | R20.4 — Call step type in sequences (amends R1.1) | R20 — Notes, suggestions & calling (Sales + Marketing) | Sequences currently only support email/LinkedIn/wait/task steps (see R1.1 in the existing outreach-loop backlog). Add a call step type: it materializes as a due task at its point in the cadence, and if Twilio is connected, offers a one-click “Call now” action right from the step. This directly extends an already-in-progress Track A ticket, so coordinate with whoever owns sequences before starting. Acceptance criteria: (1) sequence_steps.stepType accepts call alongside the existing values. (2) The enrollment scheduler materializes a call step as a due task at the right point in the cadence, the same way it already does for the task step type. (3) If Twilio (R20.2) is connected, the step shows “Call now” and logs the call automatically on completion. (4) If Twilio isn't connected, the step still works as a manual task with a disposition field (connected / no answer / voicemail / bad number). (5) The call's disposition can branch or advance the sequence, the same way reply/bounce branching already works. | to do | Low | 11 | 5 | outreach,backend,frontend | outreach | backend,frontend | R1.1, R1.2 (Track A); R20.1, R20.2; R21.1 | 86d3wzk00 | https://app.clickup.com/t/90161651543/86d3wzk00 | Neeraj Singh | to do | Yes
R16.1 | R16.1 — Calendar OAuth sync (Google first) | R16 — Meeting bot + calendar sync | Let users connect their Google Calendar (Outlook as a stretch goal) so upcoming meetings automatically show up tied to the right prospect/company, matched by attendee email address. Acceptance criteria: (1) OAuth connect flow stores encrypted tokens the same way the existing inbox-connect flow does. (2) Meetings are matched to a prospect by attendee email and shown on that prospect's/company's detail page. (3) Two-way sync (a meeting created in Skout appearing on the user's calendar) is a stretch goal, not required for v1. | to do | Low | 12 | 8 | platform,backend,infra | platform | backend,infra | none |  |  |  |  | No
R16.2 | R16.2 — Meeting bot join + notes | R16 — Meeting bot + calendar sync | Integrate a meeting-bot provider (a service that can join a video call, record it, and transcribe it) so a bot can join a scheduled call tied to a Skout prospect and automatically produce a summary and action items attached to that prospect's activity timeline. Must show a clear recording/consent disclosure, since call recording has legal requirements. Acceptance criteria: (1) The bot auto-joins meetings tagged for a Skout prospect (opt-in, per-meeting or workspace-wide). (2) A transcript summary and action items post to the activity timeline within a few minutes of the call ending. (3) Recording/transcript storage includes a visible consent disclosure banner. | to do | Low | 12 | 13 | ai,backend,infra | platform | ai-service,backend,infra | R16.1 | 86d3wzk02 | https://app.clickup.com/t/90161651543/86d3wzk02 | Neeraj Singh | to do | Yes
R16.3 | R16.3 — Meeting notes → auto-fill | R16 — Meeting bot + calendar sync | Take the meeting summary from R16.2 and extract specific, typed fields from it — next steps, any stated budget or timeline, stakeholders mentioned — instead of leaving it as one block of text, so this structured data can feed the auto-fill pipeline (R13.3). Acceptance criteria: (1) Extraction produces typed fields (not a raw text dump), each with a confidence value. (2) The extracted fields feed R13.3's auto-fill pipeline tagged with source = meeting_bot. | to do | Low | 12 | 5 | ai,backend | ai | ai-service,backend | R16.2; R13.3 | 86d3wzk04 | https://app.clickup.com/t/90161651543/86d3wzk04 | Neeraj Singh | to do | Yes
R20.3 | R20.3 — AI next-best-action suggestions | R20 — Notes, suggestions & calling (Sales + Marketing) | After a note, call, or meeting gets logged, have the AI suggest a next action — a follow-up email, a task, or adding the prospect to a sequence — based on what was said and the prospect's current score/signals. Should work the same way for both sales and marketing use cases. Acceptance criteria: (1) A suggestion is generated from the note's content plus the prospect's score/signals. (2) A one-click “accept” converts the suggestion straight into a task or sequence enrollment. (3) Every suggestion (accepted or not) is logged so the acceptance rate can be measured as a product metric. | to do | Low | 12 | 8 | ai,backend,frontend | ai | ai-service,backend,frontend | R20.1; R13.4 | 86d3wzk05 | https://app.clickup.com/t/90161651543/86d3wzk05 | Neeraj Singh | to do | Yes
R15.1 | R15.1 — DexterAI chat surface + tool registry (v0) | R15 — DexterAI agent (Phase 1 MVP) | Build the first version of Skout's named AI agent, DexterAI: a chat entry point wired to a small, fixed set of tools (search_prospects, summarize_list, explain_score) via LLM function-calling. This version is read-only — it does not take any actions on the user's behalf yet, and it must never fabricate an answer it can't ground in real tool output. Acceptance criteria: (1) POST /ai/dexter/query routes natural-language input to one of the registered tools via function-calling. (2) Every response states which tool/data it used to answer — no ungrounded answers. (3) If a user asks for something outside the current tool set, DexterAI says so honestly instead of guessing or hallucinating an action. | to do | Low | 13 | 8 | ai,ai-service,backend | ai | ai-service,backend | existing search/scoring services |  |  |  |  | No
R15.2 | R15.2 — DexterAI write actions (guarded) | R15 — DexterAI agent (Phase 1 MVP) | Extend DexterAI beyond read-only answers with exactly one write action to start: “enroll this list in sequence X.” Because this changes real data, it must always show the user a confirmation card describing exactly what it's about to do before it executes — never a silent action. Acceptance criteria: (1) Any write action renders a confirmation card the user must approve before it executes. (2) Every executed action is logged to an AI audit trail recording that DexterAI acted on behalf of the specific user. | to do | Low | 13 | 5 | ai,backend | ai | backend | R15.1; existing sequence enrollment API | 86d3wzk09 | https://app.clickup.com/t/90161651543/86d3wzk09 | Neeraj Singh | to do | Yes
R15.3 | R15.3 — DexterAI UI + onboarding | R15 — DexterAI agent (Phase 1 MVP) | Give DexterAI a persistent home in the product: a chat panel accessible from anywhere in the app, with example prompts on first open so users understand what it can (and can't yet) do. Acceptance criteria: (1) Chat panel is reachable from any workspace page. (2) On first open, 3 example prompts are shown (e.g. “Show me my strongest leads this week”). (3) Empty and error states are designed, not left blank. | to do | Low | 13 | 5 | ai,frontend | ai | frontend | R15.1 | 86d3wzk0b | https://app.clickup.com/t/90161651543/86d3wzk0b | Neeraj Singh | to do | Yes
R19.1 | R19.1 — Admin-gated rollup API | R19 — CRO Copilot (Admin-only) | Build a team-level rollup endpoint restricted to the owner/admin role — a read-only aggregate view of pipeline, activity, and signal data across the whole team, distinct from an individual rep's own view. No per-rep write actions in this phase. Acceptance criteria: (1) GET /api/v1/cro/summary returns team-level metrics (activation rate, response rate, top at-risk accounts, TAM coverage) and returns 403 for the member role. (2) Nothing in this endpoint allows writing to another rep's records. | to do | Low | 14 | 8 | ai,backend,platform | ai | backend | R12.2; R18; existing workspace role model | 86d3wzk0j | https://app.clickup.com/t/90161651543/86d3wzk0j | Neeraj Singh | to do | Yes
R19.2 | R19.2 — CRO Copilot chat (NL over the rollup) | R19 — CRO Copilot (Admin-only) | Reuse the same tool-calling chat pattern built for DexterAI (R15.1), but scope its tool set to admin-only aggregate questions like “which reps are behind on pipeline this week,” and enforce the admin role check on every single call, not just at the page level. Acceptance criteria: (1) Shares the underlying chat infrastructure with R15.1, but uses an admin-only tool set with a role check on every call. (2) Every answer is grounded in the R19.1 rollup data — no team member's individual data leaks to a non-admin. | to do | Low | 14 | 5 | ai,backend | ai | ai-service,backend | R19.1; R15.1 | 86d3wzk0h | https://app.clickup.com/t/90161651543/86d3wzk0h | Neeraj Singh | to do | Yes
R19.3 | R19.3 — CRO dashboard UI | R19 — CRO Copilot (Admin-only) | Build the admin-only dashboard page itself: pipeline rollup, top at-risk accounts, TAM coverage, and the internal moat metrics from R14.3, all in one place. Acceptance criteria: (1) The /admin/cro route returns 403 for non-admin roles at both the API and navigation level (should not appear in nav for a non-admin). (2) The page pulls data from R19.1 and R14.3. | to do | Low | 14 | 5 | frontend,platform | platform | frontend | R19.1; R14.3 | 86d3wzk0m | https://app.clickup.com/t/90161651543/86d3wzk0m | Neeraj Singh | to do | Yes
R22.3 | R22.3 — Import sequences/cadences from Apollo (stretch) | R22 — GTM platform import (Apollo.io + others) | Stretch goal: where Apollo's API exposes it, import a user's existing sequence/cadence step structure — not just their contacts — as a starting draft for a new Skout sequence, so switchers don't have to rebuild their cadences from scratch by hand. Acceptance criteria: (1) Apollo sequence steps map onto Skout's sequence_steps (email/wait steps at minimum; call steps map onto R20.4 if shipped). (2) The imported sequence always lands in draft status for review — it must never auto-activate on import. | to do | Low | 15 | 8 | platform,backend | platform | backend | R22.1; R1.1 (Track A) | 86d3wzk0n | https://app.clickup.com/t/90161651543/86d3wzk0n | Neeraj Singh | to do | Yes
R14.1 | R14.1 — Unified-record lock-in audit | R14 — Product moat (platform stickiness) | This is a written audit, not new code: go through every shipped and in-progress feature (sequences, inbox, signals, TAM, meeting notes, call notes) and check whether it writes back to the same shared prospect/company record, per the product's core anti-pattern rule (no parallel/duplicate “prospect” databases). Wherever a feature currently exports or duplicates data instead of unifying it, write it down as a gap with an owner. Acceptance criteria: (1) A short written document covers every feature listed above. (2) Each identified gap has a named owner and, if it needs a fix, a linked ticket. | to do | Normal | 16 | 3 | platform,docs | platform | backend | none | 86d3wzk0r | https://app.clickup.com/t/90161651543/86d3wzk0r | Neeraj Singh | to do | Yes
R14.2 | R14.2 — “Can't do this outside Skout” checklist per epic | R14 — Product moat (platform stickiness) | A lightweight product gate, not an engineering task: for every new epic in this plan (R11–R22), require its kickoff doc to state, in one sentence, the concrete thing that only works because it lives inside Skout's unified data model (e.g. “TAM coverage funnel is only possible because enrichment, sequence, and deal data are cross-referenced in one place”). Acceptance criteria: (1) Every new epic's kickoff doc states its moat angle in one sentence before work starts. (2) Reviewed at epic planning time, not shipped as its own separate deliverable. | to do | Normal | 16 | 1 | platform,docs | platform | backend | none | 86d3wzk0u | https://app.clickup.com/t/90161651543/86d3wzk0u | Neeraj Singh | to do | Yes
R14.3 | R14.3 — Switching-cost dashboard (internal) | R14 — Product moat (platform stickiness) | Build an internal (not customer-facing) metric that tracks, over time, what percentage of a workspace's revenue workflow actually lives natively in Skout versus still round-tripping through HubSpot exports or CSV downloads. This is a leading indicator of how “sticky” the product is. Acceptance criteria: (1) A weekly metric tracks HubSpot export volume, CSV export volume, and the % of contacted prospects with a Skout-native deal/sequence link. (2) Visible to product/leadership only, not shown to customers. | to do | Low | 16 | 5 | analytics,platform | platform | backend | R7.1 (analytics pipeline) recommended, not blocking | 86d3wzk0x | https://app.clickup.com/t/90161651543/86d3wzk0x | Neeraj Singh | to do | Yes

## Epic Summary
Epic ID | Epic Name | Rationale | Area | Story Count | Total Story Points
R10 | R10 — Kill Static List (dynamic-by-default lists) | Make dynamic/smart lists the default list-creation path; static lists become an explicit, secondary option instead of the primary object. | prospecting | 3 | 16
R11 | R11 — Signal expansion (tech signals + overlays) | Broaden signals beyond intent/hiring to tech-stack changes, store them in one unified place, and surface them visually instead of burying them in a filter panel. | corpus | 3 | 18
R12 | R12 — Build TAM (Total Addressable Market) | Turn the ICP into a sized, saved, trackable account universe with a coverage funnel and a dedicated view. | prospecting | 3 | 21
R13 | R13 — Automation core (auto-actions + auto-filled fields) | Remove manual steps: auto re-score on ICP change, auto-route AI drafts, auto-fill CRM fields, and score/signal-triggered auto-activation. | automation | 4 | 29
R14 | R14 — Product moat (platform stickiness) | Audit and metric work (not new UI) ensuring every feature deepens lock-in to the unified record instead of exporting/duplicating data. | platform | 3 | 9
R15 | R15 — DexterAI agent (Phase 1 MVP) | A narrow, grounded AI chat agent (search/summarize/explain-score) with one guarded write action, not the full PRD copilot. | ai | 3 | 18
R16 | R16 — Meeting bot + calendar sync | Google Calendar OAuth sync plus a bot that joins calls, transcribes, and posts a summary to the prospect timeline. | platform | 3 | 26
R17 | R17 — Notifications, SDR reminders & auto-alerts | New platform infrastructure: an in-app notification center, task/sequence reminders, and signal-triggered SDR alerts with email/Slack delivery. | platform | 4 | 23
R18 | R18 — Risk detection | Scoped-down MVP of deal-coach risk signals: engagement-decay flags and negative-signal flags with plain-language reasons. | ai | 2 | 16
R19 | R19 — CRO Copilot (Admin-only) | A restricted, read-only, exec-facing rollup (API + chat + dashboard) gated to the owner/admin role, distinct from the SDR-facing DexterAI. | ai | 3 | 18
R20 | R20 — Notes, suggestions & calling (Sales + Marketing) | Call notes capture, Twilio click-to-call, AI next-best-action suggestions, and a new call step type in sequences. | platform | 4 | 26
R21 | R21 — Tasks | A native task entity (Skout doesn't have one today) with CRUD, rep-facing views, and reminder wiring. | platform | 3 | 13
R22 | R22 — GTM platform import (Apollo.io + others) | Let users migrate existing contacts/lists (and, as a stretch, sequences) out of Apollo.io or similar tools and into Skout. | platform | 3 | 21
CC | Cross-cutting — Sharpen features (quality bar) | Not a build epic — a quality bar applied to every epic above via a PR-template checklist. | platform | 1 | 2
TOTAL |  |  |  | 42 | 256

## ClickUp Setup Notes
Skout AI — Phase 1 Track B — ClickUp Import Notes
This workbook covers the 18 strategic Phase 1 additions (R10–R22 + cross-cutting) from
docs/tickets/phase-1-feature-work-plan.md. It does NOT re-list Track A (R1–R9, the outreach
loop already in progress) — that backlog lives in remaining-features-clickup-import.csv and
should be imported separately if not already in ClickUp.
Setup steps
1. Create a Space: Skout AI — Phase 1 (or reuse the existing Skout AI space).
2. Create one List per Epic (use the “List” column values from the Tasks sheet, e.g.
“R10 — Kill Static List (dynamic-by-default lists)”) — 13 epic lists + 1 cross-cutting list.
3. Enable Sprint Points (Settings → ClickApps) with values 1, 2, 3, 5, 8, 13.
4. Create Custom Fields:
• Area — Dropdown: prospecting, corpus, ai, automation, platform, outreach
• Surface — Dropdown: backend, frontend, ai-service, infra, integrations
• Sequence Group — Number (1–16; matches the build-order groups in the plan doc §6)
5. Import Tasks (ClickUp Import) via Settings → Import → Spreadsheet, upload this .xlsx,
and map columns:
xlsx column ClickUp field
Task Name Task Name
Description Description
List List (creates/matches the epic lists from step 2)
Status Status (map “to do” to your default open status)
Priority Priority (High=2, Normal=3, Low=4 in ClickUp's own scale)
Story Points Sprint Points
Tags Tags
Area Custom Field: Area
Surface Custom Field: Surface
Sequence Group Custom Field: Sequence Group
Dependencies (not directly importable — link manually post-import using
the Task ID values as a reference; ClickUp's native
“waiting on / blocking” relation)
6. Sort/execute within each list by the Sequence Group field — lower numbers first.
Group numbers mirror the build-sequencing order in §6 of the plan doc: 1 = foundational
(Tasks entity, notification center), 16 = ongoing/parallel (moat audits).
Notes for reviewers
• Every task's Description already includes its Acceptance Criteria inline, numbered (1), (2), (3)…
— written to be self-explanatory for a developer picking it up cold, without needing to
open the source planning doc.
• R20.4 (“Call step type in sequences”) amends the existing Track A epic R1.1 — flagged in its
own Description and Dependencies. Coordinate with whoever owns Track A before starting it.
• R22.1 (Apollo.io import) is unrelated to Skout's existing internal use of the Apollo API as an
enrichment data provider — different credentials, different code path. Called out in the
Description to avoid the two being conflated during implementation.
• Source: docs/tickets/phase-1-feature-work-plan.md §5 (“Epics & stories — Track B”).

## My Tickets (Neeraj Singh)
Task ID | Task Name | List | ClickUp URL | ClickUp Status | Priority | Story Points | Sequence Group | Description | Dependencies
R17.4 | R17.4 — Email/Slack delivery channel | R17 — Notifications, SDR reminders & auto-alerts | https://app.clickup.com/t/90161651543/86d3wzjzb | to do | Normal | 5 | 5 | In-app notifications only reach a user who's logged in. Add delivery outside the app — at minimum email, and Slack if the workspace has it connected — for high-priority alerts, so an SDR doesn't miss a hot signal just because they weren't in the tab. Acceptance criteria: (1) Each notification type has a per-user channel preference (in-app / email / both). (2) If outside delivery fails, that never blocks the in-app notification from being created. | R17.1
R13.3 | R13.3 — Auto-filled CRM/contact fields | R13 — Automation core (auto-actions + auto-filled fields) | https://app.clickup.com/t/90161651543/86d3wzjzw | to do | Normal | 8 | 10 | When enrichment, meeting notes, or call notes produce structured information about a prospect (title changes, stated budget, next steps, etc.), that data should populate the relevant contact/company fields automatically instead of requiring someone to type it in by hand. Always show where an auto-filled value came from, and always let a human's manual edit win. Acceptance criteria: (1) Auto-fill writes into the prospect's snapshot record with a source (enrichment / meeting_bot / call_note) and a confidence value. (2) Auto-filled fields are visually distinguished in the UI from fields a human typed in. (3) A user's manual edit is never silently overwritten by a later auto-fill. | existing enrichment pipeline; R16.2; R20.1
R13.4 | R13.4 — Auto-activation rules (score threshold → action) | R13 — Automation core (auto-actions + auto-filled fields) | https://app.clickup.com/t/90161651543/86d3wzjzv | to do | Normal | 8 | 10 | Let a workspace define simple, explicit rules that trigger an action automatically once a prospect crosses a score threshold or matches a signal — e.g. “score ≥ 80 and hiring signal present → auto-enroll in this sequence.” This is a small, fixed rule engine, not a general workflow builder — capped so it can't run away unsupervised. Acceptance criteria: (1) A rule combines a score threshold and/or a signal match with a target action (activate, add to list, enroll in sequence). (2) A workspace can have at most 5 active rules at a time (safety guardrail). (3) Every action a rule takes is logged and can be manually reversed (unenroll, remove from list). | R13.1; existing sequence enrollment API
R20.2 | R20.2 — Dialer/calling integration (Twilio) | R20 — Notes, suggestions & calling (Sales + Marketing) | https://app.clickup.com/t/90161651543/86d3wzjzy | to do | Normal | 8 | 11 | Wire up click-to-call from a prospect's record using Twilio (already on the platform's MVP integration list), so a rep can dial directly from Skout instead of switching to another tool, and have the call's duration/outcome logged automatically. Acceptance criteria: (1) Click-to-call initiates the call via Twilio and logs it with duration and disposition automatically, no manual re-entry. (2) The recording (where legally permitted in that jurisdiction) attaches to the corresponding note. | R20.1
R20.4 | R20.4 — Call step type in sequences (amends R1.1) | R20 — Notes, suggestions & calling (Sales + Marketing) | https://app.clickup.com/t/90161651543/86d3wzk00 | to do | Low | 5 | 11 | Sequences currently only support email/LinkedIn/wait/task steps (see R1.1 in the existing outreach-loop backlog). Add a call step type: it materializes as a due task at its point in the cadence, and if Twilio is connected, offers a one-click “Call now” action right from the step. This directly extends an already-in-progress Track A ticket, so coordinate with whoever owns sequences before starting. Acceptance criteria: (1) sequence_steps.stepType accepts call alongside the existing values. (2) The enrollment scheduler materializes a call step as a due task at the right point in the cadence, the same way it already does for the task step type. (3) If Twilio (R20.2) is connected, the step shows “Call now” and logs the call automatically on completion. (4) If Twilio isn't connected, the step still works as a manual task with a disposition field (connected / no answer / voicemail / bad number). (5) The call's disposition can branch or advance the sequence, the same way reply/bounce branching already works. | R1.1, R1.2 (Track A); R20.1, R20.2; R21.1
R16.2 | R16.2 — Meeting bot join + notes | R16 — Meeting bot + calendar sync | https://app.clickup.com/t/90161651543/86d3wzk02 | to do | Low | 13 | 12 | Integrate a meeting-bot provider (a service that can join a video call, record it, and transcribe it) so a bot can join a scheduled call tied to a Skout prospect and automatically produce a summary and action items attached to that prospect's activity timeline. Must show a clear recording/consent disclosure, since call recording has legal requirements. Acceptance criteria: (1) The bot auto-joins meetings tagged for a Skout prospect (opt-in, per-meeting or workspace-wide). (2) A transcript summary and action items post to the activity timeline within a few minutes of the call ending. (3) Recording/transcript storage includes a visible consent disclosure banner. | R16.1
R16.3 | R16.3 — Meeting notes → auto-fill | R16 — Meeting bot + calendar sync | https://app.clickup.com/t/90161651543/86d3wzk04 | to do | Low | 5 | 12 | Take the meeting summary from R16.2 and extract specific, typed fields from it — next steps, any stated budget or timeline, stakeholders mentioned — instead of leaving it as one block of text, so this structured data can feed the auto-fill pipeline (R13.3). Acceptance criteria: (1) Extraction produces typed fields (not a raw text dump), each with a confidence value. (2) The extracted fields feed R13.3's auto-fill pipeline tagged with source = meeting_bot. | R16.2; R13.3
R20.3 | R20.3 — AI next-best-action suggestions | R20 — Notes, suggestions & calling (Sales + Marketing) | https://app.clickup.com/t/90161651543/86d3wzk05 | to do | Low | 8 | 12 | After a note, call, or meeting gets logged, have the AI suggest a next action — a follow-up email, a task, or adding the prospect to a sequence — based on what was said and the prospect's current score/signals. Should work the same way for both sales and marketing use cases. Acceptance criteria: (1) A suggestion is generated from the note's content plus the prospect's score/signals. (2) A one-click “accept” converts the suggestion straight into a task or sequence enrollment. (3) Every suggestion (accepted or not) is logged so the acceptance rate can be measured as a product metric. | R20.1; R13.4
R15.2 | R15.2 — DexterAI write actions (guarded) | R15 — DexterAI agent (Phase 1 MVP) | https://app.clickup.com/t/90161651543/86d3wzk09 | to do | Low | 5 | 13 | Extend DexterAI beyond read-only answers with exactly one write action to start: “enroll this list in sequence X.” Because this changes real data, it must always show the user a confirmation card describing exactly what it's about to do before it executes — never a silent action. Acceptance criteria: (1) Any write action renders a confirmation card the user must approve before it executes. (2) Every executed action is logged to an AI audit trail recording that DexterAI acted on behalf of the specific user. | R15.1; existing sequence enrollment API
R15.3 | R15.3 — DexterAI UI + onboarding | R15 — DexterAI agent (Phase 1 MVP) | https://app.clickup.com/t/90161651543/86d3wzk0b | to do | Low | 5 | 13 | Give DexterAI a persistent home in the product: a chat panel accessible from anywhere in the app, with example prompts on first open so users understand what it can (and can't yet) do. Acceptance criteria: (1) Chat panel is reachable from any workspace page. (2) On first open, 3 example prompts are shown (e.g. “Show me my strongest leads this week”). (3) Empty and error states are designed, not left blank. | R15.1
R19.1 | R19.1 — Admin-gated rollup API | R19 — CRO Copilot (Admin-only) | https://app.clickup.com/t/90161651543/86d3wzk0j | to do | Low | 8 | 14 | Build a team-level rollup endpoint restricted to the owner/admin role — a read-only aggregate view of pipeline, activity, and signal data across the whole team, distinct from an individual rep's own view. No per-rep write actions in this phase. Acceptance criteria: (1) GET /api/v1/cro/summary returns team-level metrics (activation rate, response rate, top at-risk accounts, TAM coverage) and returns 403 for the member role. (2) Nothing in this endpoint allows writing to another rep's records. | R12.2; R18; existing workspace role model
R19.2 | R19.2 — CRO Copilot chat (NL over the rollup) | R19 — CRO Copilot (Admin-only) | https://app.clickup.com/t/90161651543/86d3wzk0h | to do | Low | 5 | 14 | Reuse the same tool-calling chat pattern built for DexterAI (R15.1), but scope its tool set to admin-only aggregate questions like “which reps are behind on pipeline this week,” and enforce the admin role check on every single call, not just at the page level. Acceptance criteria: (1) Shares the underlying chat infrastructure with R15.1, but uses an admin-only tool set with a role check on every call. (2) Every answer is grounded in the R19.1 rollup data — no team member's individual data leaks to a non-admin. | R19.1; R15.1
R19.3 | R19.3 — CRO dashboard UI | R19 — CRO Copilot (Admin-only) | https://app.clickup.com/t/90161651543/86d3wzk0m | to do | Low | 5 | 14 | Build the admin-only dashboard page itself: pipeline rollup, top at-risk accounts, TAM coverage, and the internal moat metrics from R14.3, all in one place. Acceptance criteria: (1) The /admin/cro route returns 403 for non-admin roles at both the API and navigation level (should not appear in nav for a non-admin). (2) The page pulls data from R19.1 and R14.3. | R19.1; R14.3
R22.3 | R22.3 — Import sequences/cadences from Apollo (stretch) | R22 — GTM platform import (Apollo.io + others) | https://app.clickup.com/t/90161651543/86d3wzk0n | to do | Low | 8 | 15 | Stretch goal: where Apollo's API exposes it, import a user's existing sequence/cadence step structure — not just their contacts — as a starting draft for a new Skout sequence, so switchers don't have to rebuild their cadences from scratch by hand. Acceptance criteria: (1) Apollo sequence steps map onto Skout's sequence_steps (email/wait steps at minimum; call steps map onto R20.4 if shipped). (2) The imported sequence always lands in draft status for review — it must never auto-activate on import. | R22.1; R1.1 (Track A)
R14.1 | R14.1 — Unified-record lock-in audit | R14 — Product moat (platform stickiness) | https://app.clickup.com/t/90161651543/86d3wzk0r | to do | Normal | 3 | 16 | This is a written audit, not new code: go through every shipped and in-progress feature (sequences, inbox, signals, TAM, meeting notes, call notes) and check whether it writes back to the same shared prospect/company record, per the product's core anti-pattern rule (no parallel/duplicate “prospect” databases). Wherever a feature currently exports or duplicates data instead of unifying it, write it down as a gap with an owner. Acceptance criteria: (1) A short written document covers every feature listed above. (2) Each identified gap has a named owner and, if it needs a fix, a linked ticket. | none
R14.2 | R14.2 — “Can't do this outside Skout” checklist per epic | R14 — Product moat (platform stickiness) | https://app.clickup.com/t/90161651543/86d3wzk0u | to do | Normal | 1 | 16 | A lightweight product gate, not an engineering task: for every new epic in this plan (R11–R22), require its kickoff doc to state, in one sentence, the concrete thing that only works because it lives inside Skout's unified data model (e.g. “TAM coverage funnel is only possible because enrichment, sequence, and deal data are cross-referenced in one place”). Acceptance criteria: (1) Every new epic's kickoff doc states its moat angle in one sentence before work starts. (2) Reviewed at epic planning time, not shipped as its own separate deliverable. | none
R14.3 | R14.3 — Switching-cost dashboard (internal) | R14 — Product moat (platform stickiness) | https://app.clickup.com/t/90161651543/86d3wzk0x | to do | Low | 5 | 16 | Build an internal (not customer-facing) metric that tracks, over time, what percentage of a workspace's revenue workflow actually lives natively in Skout versus still round-tripping through HubSpot exports or CSV downloads. This is a leading indicator of how “sticky” the product is. Acceptance criteria: (1) A weekly metric tracks HubSpot export volume, CSV export volume, and the % of contacted prospects with a Skout-native deal/sequence link. (2) Visible to product/leadership only, not shown to customers. | R7.1 (analytics pipeline) recommended, not blocking